## Summary
BRD Time Tracker — Remediation Issue Tracker
Generated | 2026-04-18
Source | RISK_REMEDIATION.md
Totals
Total issues | 23
Critical | 7
Important | 11
Low | 5
Status breakdown
Not Started | 23
In Progress | 0
Done | 0
Blocked | 0
Roadmap windows
Week 1 (Critical fixes) | 2026-04-20 to 2026-04-24
Week 2 (Important fixes) | 2026-04-27 to 2026-05-01
Month 2 (Ideal architecture) | 2026-05-04 to 2026-05-22
Ongoing / background | 2026-05-25 onward

## Issues Tracker
Sno | Title | Issue Description | Severity | Assignee | Start Date | End Date | Status
1 | Webhook HMAC signatures for Edge Functions | screenshot-webhook and activity-webhook have verify_jwt=false and no HMAC. Any actor with the URL can POST into any tenant's data. Add HMAC-SHA256 signature + timestamp header and verify with crypto.timingSafeEqual. Per-org secret stored in organizations.webhook_secret. | Critical | Security Engineer | 2026-04-20 | 2026-04-20 | Not Started
2 | Enforce table allowlist in Forge proxy | forge-proxy-controller.js only logs warnings on sensitive tables. Service-role client bypasses RLS. Convert SENSITIVE_TABLES to a hard PROXY_POLICY allowlist with per-table ops, required filters, and column allowlists. Default-deny. | Critical | Backend Engineer | 2026-04-20 | 2026-04-20 | Not Started
3 | Add Postgres advisory lock around background services | activity-polling (setInterval 3min), clustering (setTimeout daily), notifications services are single-instance with no distributed lock. Under Cloud Run scale-out they duplicate work and load. Wrap each tick in pg_try_advisory_lock(hashtext(serviceName)). | Critical | Backend Engineer | 2026-04-21 | 2026-04-21 | Not Started
4 | Move admin dashboard sessions to Supabase table | admin-dashboard-controller.js stores sessions in a Map. Cloud Run horizontal scaling / deploys wipe sessions. Create admin_sessions table, wrap set/get/delete in an adminSessionStore module, keep 30s in-process LRU cache for latency. | Critical | Backend Engineer | 2026-04-22 | 2026-04-22 | Not Started
5 | Remove asApp() fallback in scheduled worklog sync | scheduledWorklogSync.js falls back to createJiraWorklogAsApp when asUser throws AUTH_TYPE_UNAVAILABLE, breaking per-user attribution (the product's core value). Write a PENDING row instead so interactive sync creates the worklog with correct user attribution on next app open. | Critical | Forge/Backend Engineer | 2026-04-23 | 2026-04-23 | Not Started
6 | Delete update-issues-cache stub Edge Function | supabase/functions/update-issues-cache/index.ts is an explicit placeholder (TODO: Implement actual cache update mechanism) that returns success without doing anything. Delete the function and any cron calling it. Forge manifest already handles cache refresh via avi:jira:updated:issue. | Important | Backend Engineer | 2026-04-27 | 2026-04-27 | Not Started
7 | Update Forge KVS clearSiteCache to enumerate keys | lifecycleService.js comment says KVS doesn't support enumeration. Outdated: @forge/kvs now supports kvs.query().where('key', WhereConditions.beginsWith(prefix)).getMany() with cursor pagination. Replace hardcoded two-key delete with query-based cleanup on uninstall. | Important | Forge Engineer | 2026-04-28 | 2026-04-28 | Not Started
8 | Add 5-minute LRU cache for Atlassian /me endpoint | atlassian-auth.js and dashboard-auth.js hit Atlassian APIs on every request (1-3 calls, ~400-900ms TTFB). Add in-process LRU keyed by sha256(token) with 5-min TTL. For dashboard-auth, cache all three results (/me, /accessible-resources, /mypermissions) together. | Important | Backend Engineer | 2026-04-28 | 2026-04-28 | Not Started
9 | Add exponential backoff to activity polling service | activity-polling-service.js has fixed 3-min interval with no backoff on failure. Track consecutive failures and multiply interval by 2x up to 30-min cap. Convert from setInterval to self-rescheduling setTimeout. | Important | Backend Engineer | 2026-04-29 | 2026-04-29 | Not Started
10 | Add size cap and auto-VACUUM for offline SQLite | OfflineManager (desktop_app.py line 2229) has no file size check, no TTL on synced rows. On startup, if DB > 500MB, delete synced rows older than 14 days and run VACUUM INTO. Prevents unbounded growth for offline or sync-blocked users. | Important | Desktop Engineer | 2026-04-29 | 2026-04-29 | Not Started
11 | Log AI confidence score and add UI transparency tooltip | activity-db-service.js uses MIN_CONFIDENCE_THRESHOLD (default 0.5) to decide assignment silently. Log confidenceScore into activity_records.metadata. Add 'Why unassigned?' tooltip in UI explaining AI confidence was below threshold. | Important | Full-Stack Engineer | 2026-04-30 | 2026-04-30 | Not Started
12 | Tighten duplicate-user heuristic to equality-only match | issueQueryService.js uses substring match on Atlassian account IDs (otherId.includes(currentId)) which can match unrelated accounts. Remove substring branch; keep email equality match only. Prepare for schema-level fix. | Important | Forge Engineer | 2026-04-30 | 2026-04-30 | Not Started
13 | Add admin email allowlist alongside password | admin-dashboard-controller.js uses a single shared ADMIN_DASHBOARD_PASSWORD. Add ADMIN_EMAIL_ALLOWLIST env var and require email + password. Stops any single env-var leak from compromising all admin access. | Important | Backend Engineer | 2026-05-01 | 2026-05-01 | Not Started
14 | Replace polling services with pg-boss on Cloud Run Jobs | Replace three self-scheduled services (activity, clustering, notifications) with pg-boss queues. Use Cloud Scheduler + Cloud Run Jobs for scheduled clustering. Provides exactly-once delivery, retries, dead-letter, and decouples worker from API scaling. | Critical | Backend / DevOps Engineer | 2026-05-04 | 2026-05-08 | Not Started
15 | Migrate server logs to Pino with structured redaction | Replace regex-based log-sanitizer with Pino redact config keyed on JSON paths (e.g. *.email, *.token). Keep existing regex as second-pass belt-and-suspenders. Emits structured JSON logs queryable in Cloud Logging. | Important | Backend Engineer | 2026-05-11 | 2026-05-13 | Not Started
16 | Replace generic Forge proxy with named RPC endpoints | Replace POST /api/forge/proxy (table/operation pattern) with named endpoints like /api/forge/activity/query, /api/forge/worklog/sync. Move business logic server-side; make API enumerable. Use a role-scoped Postgres user, not service role. | Critical | Backend Engineer | 2026-05-11 | 2026-05-15 | Not Started
17 | Migrate admin dashboard to Supabase Auth with MFA + audit log | Replace hand-rolled session tokens with Supabase Auth. Enforce admin allowlist via RLS. Enable TOTP MFA. Write every admin action to an append-only admin_audit table. | Important | Backend Engineer | 2026-05-18 | 2026-05-20 | Not Started
18 | Fix duplicate users/orgs in schema + one-time data migration | Merge duplicate organizations by jira_cloud_id into oldest row; merge duplicate users by (organization_id, atlassian_account_id). Add unique constraints. Delete the heuristic dual-read code in issueQueryService and scheduledWorklogSync once clean. | Important | Backend / Data Engineer | 2026-05-18 | 2026-05-22 | Not Started
19 | Document CORS no-origin allow as deliberate design choice | ai-server/src/index.js allows no-origin requests for desktop/Forge/server-to-server clients. This is correct but not a security boundary. Expand existing comment to enumerate the three callers and clarify auth is enforced in middleware. | Low | Backend Engineer | 2026-05-25 | 2026-05-25 | Not Started
20 | Document desktop secure-storage threat model | secure_storage.py already uses OWASP-compliant PBKDF2+AES fallback. Add python-desktop-app/SECURITY.md clarifying threat model: defends against cold-disk extraction and cross-machine copying; does not defend against malware running as the user. | Low | Desktop / Security Engineer | 2026-05-25 | 2026-05-25 | Not Started
21 | Secure /reset-upload-lock endpoint with admin auth + rate limit | Require admin auth, add 1/min rate limit per user, log every call to admin audit log with caller and target upload ID. | Low | Backend Engineer | 2026-05-26 | 2026-05-26 | Not Started
22 | Establish quarterly log-sanitizer pattern review | Add to engineering runbook: quarterly grep diff of logger.info¦warn¦error call sites vs. sanitizer patterns in log-sanitizer.js. Catches drift when new sensitive fields are added. | Low | Backend Engineer | 2026-05-27 | 2026-05-27 | Not Started
23 | Incrementally split desktop_app.py into modules | 563 KB single-file Python app hurts onboarding and test coverage. Split opportunistically by responsibility (tray/, capture/, sync/, idle/) as areas are touched. No big-bang rewrite. | Low | Desktop Engineer | 2026-06-01 | 2026-06-30 | Not Started